## Sheet1
TIMELINES-HISTORY OF SS IMPLEMENTATION |  |  |  | CAPACITY DEVELOPMENT AND SUSTAINABILITY
COUNTRY | YEAR (from initial implementation till 2010 | NAME OF SS COMMUNITIES (PAST AND ACTIVE) | PARTICIPANT #S BREAKDOWN (BY 4 PEER GROUPS) | IMPLEMENTING ORGANISATION AND OTHER ORG. THAT YOU HAVE PARTNERED/COLLABORATED WITH | SS RESOURCES DEVELOPED/USED | KEY EMERGING ISSUES/CHALLENGES | LESSONS LEARNED/ACTIONS TAKEN | SS FUNDING SOURCE UTILISED | CAPACITY NEEDS IDENTIFIED
Chuuk State Federated State of Micronesia 2010 May Nov |  | Iras/Penia/Nepukos | Young men/Young Women/ | Chuuk HIV/STI Program | Funding from Office | Facilitators don't | Appropriate ways
|  | Beach Side/Nepukos | Older men/Older Women | Chuuk Women Council | of Minority Health | feel comfortable | of selecting facilitators
|  | Mountain Side | total of 289. | Village leaders of the | Resource Center | facilitating/danger | er | Health Resource
|  |  | Young men=64 Older men 55 | SS communities | Facilitators compen | for core group | Selection Criters with | Center.
|  |  | Younger women= 87 |  | sation/Training Su | during evening to
|  |  | Older womne =83 |  | uplies from NSP | the rural villages | cacreful seletion.
[5 empty] | fully supported | community events
[6 empty] | delays implem. | Core Group took the
[6 empty] | Wrong facilitators | role of the facilitators
to train, : preacher
[6 empty] | cannot preach | Beach Side was selected
[6 empty] | due to sensitive | for conveniency/safety
[6 empty] | issues on sex. | to replace Neawo
Time consume/
lack of comunicatio
between facilitator
[6 empty] | and core group | SS is now included in
the Chuuk HIV/STI
Strategic Plan 2011
for 2 communities